## Sheet1
Sl no | Projects | Status | Start date | End date | Amount (Million) | Project duriation (Months) | Value for each month | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
[8 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1 | A | Completed | 2017-01-01 | 2018-06-01 | 54 | 18 | 3 | 2017 J: 3; 2017 F: 3; 2017 M: 3; 2017 A: 3; 2017 M: 3; 2017 J: 3; 2017 J: 3; 2017 A: 3; 2017 S: 3; 2017 O: 3; 2017 N: 3; 2017 D: 3; 2018 J: 3; 2018 F: 3; 2018 M: 3; 2018 A: 3; 2018 M: 3; 2018 J: 3
2 | B | Completed | 2017-05-01 | 2019-04-01 | 96 | 24 | 4 | 2017 M: 4; 2017 J: 4; 2017 J: 4; 2017 A: 4; 2017 S: 4; 2017 O: 4; 2017 N: 4; 2017 D: 4; 2018 J: 4; 2018 F: 4; 2018 M: 4; 2018 A: 4; 2018 M: 4; 2018 J: 4; 2018 J: 4; 2018 A: 4; 2018 S: 4; 2018 O: 4; 2018 N: 4; 2018 D: 4; 2019 J: 4; 2019 F: 4; 2019 M: 4; 2019 A: 4
3 | C | Ongoing | 2018-08-01 | Juy 2020 | 120 | 24 | 5 | 2018 A: 5; 2018 S: 5; 2018 O: 5; 2018 N: 5; 2018 D: 5; 2019 J: 5; 2019 F: 5; 2019 M: 5; 2019 A: 5; 2019 M: 5; 2019 J: 5; 2019 J: 5; 2019 A: 5; 2019 S: 5; 2019 O: 5; 2019 N: 5; 2019 D: 5; 2020 J: 5; 2020 F: 5; 2020 M: 5; 2020 A: 5; 2020 M: 5; 2020 J: 5; 2020 J: 5
4 | D | Ongoing | 2020-01-01 | 2020-12-01 | 72 | 12 | 6 | 2020 J: 6; 2020 F: 6; 2020 M: 6; 2020 A: 6; 2020 M: 6; 2020 J: 6; 2020 J: 6; 2020 A: 6; 2020 S: 6; 2020 O: 6; 2020 N: 6; 2020 D: 6
5 | Turnover in each year | [6 empty] | 2017 J: 68; 2018 J: 91; 2019 J: 76
6 | % of Inflation | [6 empty] | 2017 J: 10%; 2018 J: 5%; 2019 J: 0%
7 | Infaltion amount | [6 empty] | 2017 J: 6.8; 2018 J: 4.55; 2019 J: 0
8 | Total Turnover in each year | [6 empty] | 2017 J: 74.97; 2018 J: 95.55; 2019 J: 76
9 | Average turn over (A)= | [6 empty] | 2017 J: 82.1733
| E | To be tendered | 2020-04-01 | 2023-03-01 | 250 |  |  | 2020 A: Work to be tendered
| Overlaps | [6 empty] | 2020 A: 5; 2020 M: 5; 2020 J: 5; 2020 J: 5
[47 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| Over lap amount(B) | [6 empty] | 2020 A: 74
[23 empty] | A= | 100
| average turnover = | [6 empty] | 2017 J: 1714050516; 2018 A: N=; 2018 M: 1.5
[8 empty] | 5142151548 | [14 empty] | B= | 100
[23 empty] | Bid capacity= |  |  |  | 200
This portion will not be counted in calculation as 3 years is calander years.

## Sheet2
Bid capacity (25 Points)
This parameter evaluates the contractor on the capacity of his resources to take on more works in addition to what he is aready doing. A contractor can score anywhere between 0 to 25 depending on how close his capacuty is to his quoted bid. This parameter is crucial in determining wheather or not the contractor can successfuly execute the works that he is taking up given his resourceand the work he is already committed to:
Bid capacity =2*A*N-B |  | A= Annual turn over for past 3 years
N=Estimate duration of the project to be tendered
B= Portion of other ongoing works to be completed in the period that over laps with the current project's duriation(that is N)
Step | Description
1 | List all projects that the contractor has executed in the last 3 CALENDAR years
2 | Obtain the value of each of these projects per month, calculated as the total size divided by the total duration (in months)
3 | Arrange these projects clearly according to their timelines on a calendar for last 3 years
4 | For each of the last 3 calendar years note the number of months for each project
5 | Now for each of the last 3 calendar years, obtain the total quantity of work as the sum of each projects value per month and its number of months for that particular year
6 | Inflate the total value from each year by 5% to bring it to the price levels of the current year
7 | Calculate the average annual revenue A as an average of the total values of all the 3 years
8

## Step 1
Sl. No | Name of the project | Amount(Million) | Duration (in months) | Start date | End date | Value per month
1 | Project A | 54 | 18 | 2017-01-01 | 2018-06-01 | 3
2 | Project C | 96 | 24 | 2017-05-01 | 2019-04-01 | 4
3 | Project D | 120 | 24 | 2018-08-01 | 2020-07-01 | 5